## Chipsat-1 Work
ChipSat-1 Person Hours | Hours
| Sample of initial data: 2022-11 |  | Processed data
Antenna Testing E/M | 48 |  | 48
Prototyping (K) |  |  | 75
Integration (K) |  |  | 75
Software Development (K) |  |  | 75
Systems Engineering (K) | 224
Project Management (O) | 112 |  | 112
Orbital Analysis | 10 | ? | 10
Antenna Simulation | 24 | ? | 24
Test Campaign Antenna | 12 |  | 0
Test Campaign QM | 24 |  | 24
Test Campaign FM | 24 |  | 24
Person Months | 3.1447
Scenario 0: Actual
Constants | Salary/Hour |  | Init. Redesign Chance | Cumul. Redesign Chance | Cost of Redesign
| 133 |  | 25% | 25% | 12665

## ChipSat-1 Cost
Cost driver | Cost (EUR) | Iter | Details | Percentage of total costs
Breadboard model | 454 | 1,3 | Components purchase | 0,6
Structural model (SM) | 5 | 3 | The ChipSat-1 SM was built with an empty PCB and the antennas with their deployment mechanism | 0,06
EM Manufacturing + Components | 1274 | 2 | Costs from components purchasing, manufacturing, and assembly with subcontractor | 14,9
SM testing | 625 | 3 | Costs of vibration testing (detailed in Table 4) | 7,3
Interface bracket for SM testing and adapters for test platform | 760 | 3 | One aluminum interface bracket and two vibration test adapters (vertical + horizontal) | 8,9
QM and FM Manufacturing + Components | 1392 | 4 | Costs from components purchasing, manufacturing, and assembly with subcontractor | 16,3
ChipSat-1 qualification | 1300 | 4 | Costs of qualification testing, random vibration + thermal vacuum and thermal cycling (detailed in Table 4) | 15,2
ChipSat-1 acceptance | 1300 | 5 | Costs of acceptance testing, random vibrations (detailed in Table 4) | 15,2
Interface bracket with payload and qualification and acceptance test adapters Obsolete brackets and adapters after late design changes | 580 | 3
Interface bracket with payload and qualification and acceptance test adapters | 1240 | 4,5 | Two sets of interface brackets and qualification and acceptance tests adapters were manufactured due to last minute interface requirements change | 21,3
(580EUR spent on brackets and adapters that were obsolete after late design changes)
Total costs | 8930
8925

## POQUITO Work
POQUITO Person hours
No. | Development Time Driver | Time Spent hours
1 | Integration | 108 | 6 hours / lab session * 1 session/month * 9 months * 2 people
2 | Software Development | 40 | 2 weeks of work * person, roughly (PLATFORM only)
3 | Project Management | 226 | 3 hrs/document * 12 documents * 2 + 2hours process/procurement * 21 + 24*3 licensing/insurance + 40 hours SW/ENG equivalent
4 | Antenna Simulation | 3 | Direct report
5 | Orbital Analysis | 66 | 5 days FTE x 2 persons + 1 day FTE x 1 person
6 | Platform PCB design | 24 | 12 hours/PCB * 2 PCBs (panels+baseplate)
7 | ChipSat Development | 52
8 | ADCS Development | 104
9 | In-house soldering | 24 | 1 day (panels) + 2 days (ADCS)
10 | Test Campaign (QM) | 48 | 3 days FTE x 2 persons
11 | Test Campaign (FM) | 64 | 4 days FTE x 2 persons
| Total Time | 759
Contributors
| KK | 2023-06 to 2024-03
| AH | Lab work
| CBR | Accounted for + Lab work
| JMS | 3 months * 12hrs/week
| MA | Lab work
| NS | ADCS
| SG | Accounted for + Lab work
| SKS | 6 months * 12hrs/week
| TDc | 3 months * 12hrs/week
| VF | Accounted for + PM + Lab work

## CF Analysis
|  |  | ChipSat |  |  | AI4Space |  |  | POQUITO |  |  | ChiPySat
| Treatment | Initial Theory | External factors | Effects | Revised theory | External factors | Effects | Revised theory | External factors | Effects | Revised theory | External factors | Effects | Revised theory
1 | Bypassing structural/thermal analysis | Consistent reduction in development time, but significant increase in cost (due to test campaigns). Increase in risk (due to undetected errors). | \acs{DUT} complexity affects chance of non-conformance. | The decision to perform no analysis led to a reduction in development time and an increase in cost due to testing. | \cfnorevisions | \acs{DUT} complexity affects chance of non-conformance. Manufacturing quality. | The decision to perform no analysis led to a reduction in development time and no additional testing (in this case, due to system simplicity). | Consistent reduction in development time. Test campaigns may increase cost. Increase in risk (due to undetected errors). | \acs{DUT} complexity. Manufacturing quality. Team size. | The decision to perform no analysis led to a reduction in development time and no additional testing (in this case, due to reuse). | Consistent reduction in development time. Test campaigns may increase cost. Increase in risk (due to undetected errors). | \acs{DUT} complexity. Manufacturing quality. Team size. | The decision to perform no analysis led to a reduction in development time and no additional testing (in this case, due to reuse). | Consistent reduction in development time. Test campaigns may increase cost. Increase in risk (due to undetected errors). | Consistent reduction in development time. Test campaigns may increase cost. Increase in risk (due to undetected errors).
2 | In-house manufacturing | Total development time should decrease. Cost should decrease (assuming no external manufacturing costs). Risk should increase (assuming team not experienced in manufacturing for space) | \acs{DUT} complexity affects chance of non-conformance. Time, cost \& risk delta depend on external manufacturer. | Fixed processes, leading to almost identical results, can predictably increase/decrease development time and cost. Risk, however, depends on manufacturing capabilities, communication, and added delays. | Actual development time increases due to the added internal effort (blocking time is not modelled in this cumulative model). Cost decreases (no external manufacturing costs). Risk is project-dependent due to confounding factors. | \acs{DUT} complexity affects chance of non-conformance. Time, cost \& risk delta depend on external manufacturer. | Fixed processes, leading to almost identical results, can predictably increase/decrease development time and cost. Risk, however, depends on manufacturing capabilities, communication, and added delays. | Actual development time increases due to the added internal effort (blocking time is not modelled in this cumulative model). Cost decreases (no external manufacturing costs). Risk is project-dependent due to confounding factors. | \acs{DUT} complexity. Time, cost \& risk delta depend on external manufacturer. | Fixed processes, leading to almost identical results, can predictably increase/decrease development time and cost. Risk, however, depends on manufacturing capabilities, communication, and added delays. | Actual development time increases due to the added internal effort (blocking time is not modelled in this cumulative model). Cost decreases (no external manufacturing costs). Risk is project-dependent due to confounding factors. | \acs{DUT} complexity. Time, cost \& risk delta depend on external manufacturer. | Fixed processes, leading to almost identical results, can predictably increase/decrease development time and cost. Risk, however, depends on manufacturing capabilities, communication, and added delays. | Actual development time increases due to the added internal effort (blocking time is not modelled in this cumulative model). Cost decreases (no external manufacturing costs). Risk is project-dependent due to confounding factors.
3 | Multi-step development | Total development time should decrease (assuming a long \acs{BDUF} step). Cost should increase (due to more manufacturing runs). Risk should be project-dependent (based on whether a team can predict non-conformances early or late). | Team expertise. External/supplier requirements. | Changes in external requirements necessitated multiple iterations. Otherwise, a high initial design time prevails over year-long projects. Multiple iterations lead to a cost increase. Risk depends on the quality of the design/iterations. | \cfnorevisions | System complexity. Team expertise. | A high initial design time would prevail over the actual fast schedule of the mission, influenced by its simplicity. Multiple iterations lead to a cost increase. Risk depends on the quality of the design/iterations. | \cfnorevisions | System complexity. Team expertise. | Specific \acs{BDUF} tasks identified that would increase development time and reduce risk. Cost can be calculated by measuring the cost of added iterations. | \cfnorevisions | System complexity. Team expertise. | Specific \acs{BDUF} shortcomings identified, caused because of the software complexity and lack of specific experience, that would anyway require a second iteration. Cost can be calculated based on component prices. Risk assumed to increase due to the reduced design effort. | \cfnorevisions
4 | Short iterations | Development time should decrease. Cost should increase (due to more manufacturing runs). Risk should be project-dependent (based on project size and whether iteration length \& team size are suitable). | System complexity. Team expertise. | Development time and cost can be accurately predicted based on the times \& cost of a single iteration. Risk, however, depends on the reduction of work quality (due to less design) over each iteration. | \cfnorevisions |  |  |  | System complexity. Team expertise. | Each system-level iteration of POQUITO is associated with a base manufacturing/testing effort and cost, which increases with the number of iterations. Actual project schedule shows that baseline design effort is also required, meaning that shorter iterations would also require more iterations. Schedule and cost impact can be inferred then directly. Risk seems affected by low-level technical aspects. | Development time depends on project complexity, with shorter iterations being faster for projects of a smaller technical size. Cost increases due to manufacturing runs. Risk is project-dependent due to low-level factors. | System complexity. Team expertise. Team size. | Effects of short iterations generally linked to small team size. Cost can be calculated based on component sizes. | Development time depends on project complexity and team size. Cost increases due to manufacturing runs. Risk is project-dependent due to low-level factors. | Development time depends on project complexity and team size. Cost increases due to manufacturing runs. Risk is project-dependent due to low-level factors.
5 | Iterating over partitions | Development time should stay the same (assuming constant number of iterations). Cost should decrease (less manufacturing). Risk should increase (less early data about complete system performance). | System complexity. | Cost can be accurately predicted based on the project's cost budget. Lower initial design costs reduce development time. Risk is increased due to less initial data generated. | \cfnorevisions | System complexity. Team expertise. | The use of partitions led to a delay in manufacturing and testing a complete system. In turn, this led to later data generation for the system. The use of partitions did not generate significant \& meaningful data to be used for later. | Development time increased due to unnecessary partitioning. Cost remained similar (no more components purchased). Risk unchanged (no significant information affected system design). | System complexity. Team expertise. | The use of a partition generated engineering data to be used for later iterations (therefore reducing risk). Cost and time changes are a direct result of working on reduced versions of the system. | Development time decreased (no integration effort). Cost reduced (less manufacturing). Risk decreased (information used in later iterations before system completion). |  |  |  | Development time depends on project size. Cost may decrease (due to reduced manufacturing). Risk reduction depends on project size.
6 | Robust software framework | Development time and cost should stay the same, with reduced risk. | System complexity. Component compatibility. Team expertise. | Development time can change, based on the technical compatibility of the system with a desirable framework. No manufacturing cost associated with software. Generalised risk decrease expected based on literature. | Development time is project-dependent (based on technical compatibility). Cost should remain similar. Risk decreases due to inherent software framework characteristics. | System complexity. Component compatibility. Team expertise. | System specifications and team expertise allowed for an implementation of a more ``robust'' software framework. We identified actual non-conformances related to the software technologies used (mainly latency, unpredictability, low throughput). Other frameworks or architectures are not shown to be prone to these errors. No indications for change in development time/cost. | \cfnorevisions |  |  |  | System complexity. Team expertise. Team size. \acs{COTS} availability. | Software performance and reliability issues identified, caused by technical aspects of the chosen software architecture and technologies. Development time for software changes influenced heavily by expertise, prior work, hardware, and features. No cost change factors identified. | Development time depends on low-level factors. Cost remains similar. Risk is reduced. | Development time depends on low-level project-dependent factors. No factors influence cost. Risk decreases due to inherent software framework characteristics.
7 | Robotic Process Automation | Development time should be project-dependent (cost of automation vs.\@ less manual effort). Cost should increase (when infrastructure needed to automate testing). Risk should decrease (general assumption based on increased testing). |  |  |  | Degree of ``physicality''. Testing complexity. Team expertise. Available facilities. | Repeated testing identified regressions after software/hardware changes. Added effort for process automation counterbalanced by hypothetical repeated effort for manual testing. No hardware equipment needed for \acs{RPA}, leading to no cost change. | \cfnorevisions | Degree of ``physicality''. Testing complexity. Team size. Team expertise. Available facilities. | Manual testing procedures were not repeatable, leading to the delayed discovery of regressions. Due to the availability of equipment and tooling, \acs{RPA} would add no identifiable delays or costs. | \cfnorevisions | Degree of ``physicality''. Testing complexity. Team expertise. Available facilities. | On the one hand, manual testing procedures were not repeatable, leading to increased development time. On the other hand, due to the ``photographic'' nature of the project,\acs{RPA} would require additional effort which cannot be easily estimated. Due to the availability of equipment and tooling, \acs{RPA} would add no identifiable costs. | \cfnorevisions