## AUX
MUST
SHOULD
CAN
WON'T
N/A

## ChipSat-1 Tasks
Task | Requirement Status | Specification Date | End Date | Comment
Kick off meeting | N/A |  |  | 1 day
Resources assignment | N/A |  |  | 1 day
Mission statement | MUST | 2022-02-01 | 2022-02-14
Mechanical interface definition | N/A |  |  | Auxiliary task
Satellite orbit definition | MUST |  | 2022-03-07
ChipSat solar cell consultation | N/A |  |  | Meeting
Preliminary available power definition | SHOULD |  | 2022-02-28
ChipSat software and basic components definition | SHOULD |  | 2022-03-07
PCB high level design | MUST |  | 2022-03-07
Radio freqency licensing | MUST |  | 30.09.2022
Qualification tests definition | MUST |  | 2022-03-07
Qualification tests booking | N/A |  |  | E-mail
PCB CAD model | MUST |  | 2022-03-14 | i.e. PCB layout
Mass budget | MUST |  | 2022-03-14
Power budget | MUST |  | 2022-07-31
RF documentation | N/A
Call sign determination | N/A
Radio frequency definition | N/A
Preliminary link budget | MUST |  | 2022-02-28
Maximum antenna length definition | MUST |  | 2022-05-21
Ground station parameters determination | MUST |  | 30.06.2022
Link bugdet | MUST |  | 2022-07-31
Com. System design | MUST |  | 2022-07-31
Data compression | CAN |  |  | Never done
Wake up on light | SHOULD |  |  | Never done
Permanent storage of 211 data | SHOULD |  |  | Never done
First steps in coms | MUST |  | 2022-05-12
Measuring internal temperature | SHOULD |  | 2023-02-08
Second steps in coms | MUST |  | 2023-03-30
Packetising inter-chipsat data | MUST |  | 2023-03-16
Create low power scenarios | SHOULD |  |  | Never done
Measuring available battery | CAN |  |  | Never done
Create ambient sensor driver | SHOULD |  | 2023-02-07 | Git commit date. Issue date is 14.03.2023
Create gyroscope driver | CAN |  | 2023-03-10
Software test - sensors | N/A
Intersatellite link optimisation | CAN |  |  | Never done
Rewrite 211 in Rust | WON'T |  |  | Never done
Interface with LuxSpace | MUST
Breadboard - Mission demonstration | MUST |  | 30.06.2022
Breadboard - Sensors installation | MUST |  | 30.06.2022
Experiments with battery | SHOULD |  | 2022-08-31
Experiments with power | SHOULD |  | 30.06.2022
Eperiments with communications | N/A
Satellite PCB design (v2) | MUST |  | 2022-08-31
Satellite manufacturing of first proto-flight model | MUST |  | 2022-10-14
Satellite manufacturing (if iterations are needed) | MUST |  | 2022-12-14
Integration with ground station | MUST |  | 30.11.2022
Preliminary vibration test | N/A
Vibration Test | N/A
TVAC Test | N/A
Delivery | N/A
Add diodes to solar panels | MUST | 2022-07-20 | 2023-02-13
Fix inhibit polarity | MUST | 2023-02-13 | 2023-02-16
Replace supercap with tantalum capacitor | MUST | 2023-02-13 | 2023-02-13
Verify RF matching circuit | N/A
Check status of photodiodes | MUST | 2023-02-13 | 2023-02-16
Install photodiode DC filter | WON'T |  |  | Never done
Add more test pads | SHOULD | 2023-02-13 | 2023-02-17
Create breakoutboard with better FFC connector | MUST | 2023-02-13 | 2023-04-04
PMIC enable solder joint | MUST | 2023-02-13 | 2023-02-16
Add labels to solder jumpers | SHOULD | 2023-02-13 | 2023-02-17
Take components away from edges | SHOULD | 2023-02-13 | 2023-02-16
Check inhibit power requirements | N/A | 2023-02-13

## ChipSat-1 Trade
CF # | Name | Applied | Cost | Time | Risk
0 | Baseline |  | 8930 | 478 | Base
1 | Bypassing structural/thermal analysis | Y | 1390 | -180 | Higher
2 | Soldering PCBs in-house | N | -2000 | 72 | Lower
3 | Multi-step development | Y | 1720 | -120 | Lower
4 | Short iterations | Y | 695 | -120 | Higher
5 | Iterating over partitions | Y | -1840 | -50 | Higher
6 | Robust software framework | N | 0 | 40 | Lower

## AI4Space Trade
CF # | Name | Applied | Cost | Time | Risk
0 | Baseline |  | 4900 | 468 | Base
1 | Bypassing structural/thermal analysis | Y | 0 | -180 | Higher
2 | Soldering PCBs in-house | N | -1300 | 24 | Base
3 | Multi-step development | Y | 1300 | -265 | Base
5 | Iterating over partitions | Y | 0 | 27 | Base
6 | Robust software framework | Y | 0 | 0 | Lower
7 | Robotic Process Automation | Y | 0 | 0 | Lower

## POQUITO Trade
CF # | Name | Applied | Cost | Time | Risk
0 | Baseline |  | 26750 | 759 | Base
1 | Bypassing structural/thermal analysis | Y | 0 | -180 | Higher
2 | Soldering PCBs in-house | N | -4020 | 80 | Lower
3 | Multi-step development | Y | 7070 | -248 | Higher
4 | Short iterations | N | 3050 | 64 | Lower
5 | Iterating over partitions | Y | -1700 | -26 | Base
7 | Robotic Process Automation | N | 0 | 0 | Lower

## ChiPySat Trade
CF # | Name | Applied | Cost | Time | Risk
0 | Baseline |  | 1000 | 252 | Base
1 | Bypassing structural/thermal analysis | Y | 0 | -180 | Higher
2 | Soldering PCBs in-house | Y | -2000 | 24 | Lower
3 | Multi-step development | Y | -350 | -60 | Higher
4 | Short iterations | N | 800 | -42 | Base
6 | Robust software framework | N | 0 | -40 | Lower
7 | Robotic Process Automation | N | 0 | 40 | Lower

## Sensitivity Analysis
Project | Analysis Type | Number of Treatments | Development Time (hours) | Cost (€) | Risk (categorical)
ChipSat-1 | Actual | 4 | 478 | 8930 | 0
ChipSat-1 | Counterfactual (SCS methodology used) | 6 | 590 | 6930 | -2
ChipSat-1 | Counterfactual (SCS methodology not used) | 0 | 948 | 6965 | -2
AI4Space | Actual | 5 | 468 | 4900 | 0
AI4Space | Counterfactual (SCS methodology used) | 6 | 492 | 3600 | 0
AI4Space | Counterfactual (SCS methodology not used) | 0 | 886 | 3600 | 1
POQUITO | Actual | 3 | 759 | 26750 | 0
POQUITO | Counterfactual (SCS methodology used) | 6 | 903 | 25780 | -3
POQUITO | Counterfactual (SCS methodology not used) | 0 | 1213 | 21380 | -2
ChiPySat | Actual | 3 | 252 | 1000 | 0
ChiPySat | Counterfactual (SCS methodology used) | 6 | 210 | 1800 | -2
ChiPySat | Counterfactual (SCS methodology not used) | 0 | 468 | 3350 | -1

## ChipSat-1 Non-Comformances
# | Title | Iterations | Type | Introduction Date | Detection Date | Resolution Date | Introduction Revision | Resolution Revision
1 | Glue remaining | FM | Minor |  |  | Never | 4 | Never
2 | COMMS inadequate E2E test | FM | Minor |  |  |  | 1 | 5
3 | Deployable antenna not manufacturable | v0.1 | Major |  |  |  | 1 | 2
4 | Solar panels problematic soldering | v1.0 | Major |  |  |  | 1 | 4
5 | VCC incorrect | v1.1, fixed in FM | Minor |  |  |  | 4 | 5
6 | LED incorrect soldering | v0.1, v1.1, fixed in FM | Minor |  |  |  | 2 | 5
7 | Inhibit wired in reverse | v1.0 | Major |  |  |  | 4 | 5
8 | Solar panels wrong footprint | v0.1 | Major |  |  |  | 2 | 4
9 | OV resistor calculator error in EPS | v0.1 | Major |  |  |  | 2 | 4
10 | Missing cable infrastructure for DBG | v0.1 | Minor |  |  |  | 2 | 4
11 | Photodiode lower sensitivity than exp | FM | Minor |  |  |  | 4 | Never
12 | PCB label | v0.1 | Minor |  |  |  | 2 | 4
13 | Electrolytic Capacitor | v0.1 | Minor |  |  |  | 2 | 4
14 | Inconvenient connector | v0.1 | Minor |  |  |  | 2 | 4
15 | Incorrect diode footprint | v0.1 | Minor |  |  |  | 2 | 4
16 | Inhibit wire very difficult to solder | FM | Minor |  |  |  | 4 | Never
17 | Antenna size/design is not optimal | FM | Minor |  |  |  | 4 | Never
18 | PCB is ON by default | v0.1 | Minor |  |  |  | 2 | 4
19 | In-house designed bracket issues | v0.1 | Minor |  |  |  | 1 | 3
20 | Forgot to bring adapters | Fixed in FM | x
21 | Adapters contained non-threaded holes | Fixed in FM | Minor |  |  |  | 4 | 5
Iteration #1: Breadboard
Iteration #2: Engineering Model
Iteration #3: Breadboard
Iteration #4: Eng. Qual Model
Iteration #5: Proto-Flight Model